## Project Timeline Plan
Phase / Milestone | Task Type | Task Key | Task Title | Task Description | Start Date | End Date | Duration (Days) | Dependencies / Predecessors | Priority | Status | Team | Assignee
Phase 1: Architecture & System Specifications | Main Task |  | Power Delivery & Low-Noise Buck Architecture | Calculate total system power budget, select 3.3V/1.8V buck regulators, and size input capacitance. | 2026-10-21 | 2026-10-26 | 5 |  | HIGH | DONE | Hardware Engineering | David Miller
Phase 1: Architecture & System Specifications | Subtask |  | Buck Converter Component Selection & Simulation | Run SPICE simulations for ripple voltage under 2A pulsed load transients. | 2026-10-21 | 2026-10-24 | 3 |  | MEDIUM | DONE | Hardware Engineering | David Miller
Phase 1: Architecture & System Specifications | Subtask |  | Input Capacitance ESR & Inrush Current Calculation | Size bulk electrolytic and ceramic decoupling capacitors for minimal voltage droop. | 2026-10-23 | 2026-10-26 | 3 |  | MEDIUM | DONE | Hardware Engineering | David Miller
Phase 1: Architecture & System Specifications | Main Task |  | Microcontroller Pinout & Clock Calibration | Map all GPIO multiplexing for Cortex-M4 and route high-accuracy 16MHz crystal traces. | 2026-10-27 | 2026-11-02 | 6 | Power Delivery & Low-Noise Buck Architecture | URGENT | IN_PROGRESS | Hardware Engineering | james.wilson@sscorp.com
Phase 1: Architecture & System Specifications | Subtask |  | Oscillator Frequency Measurement on Test Points | Verify crystal PPM accuracy and load capacitance trimming. | 2026-10-27 | 2026-10-30 | 3 |  | MEDIUM | IN_PROGRESS | Hardware Engineering | james.wilson@sscorp.com
Phase 1: Architecture & System Specifications | Subtask |  | GPIO Pull-Up Stress Test under 85C Temperature | Ensure stable logic levels under elevated ambient temperature. | 2026-10-30 | 2026-11-02 | 3 |  | MEDIUM | TODO | Hardware Engineering | David Miller
Phase 1: Architecture & System Specifications | Main Task |  | System Architecture Sign-Off Gate | Formal peer review of BOM cost, power budget, and transceiver protocols. | 2026-11-03 | 2026-11-04 | 2 | Microcontroller Pinout & Clock Calibration | HIGH | TODO | Hardware Engineering | David Miller
Phase 2: Schematic Capture & Hardware Simulation | Main Task |  | High-Speed Differential Impedance Simulation (USB & CAN FD) | Model 90 Ohm USB differential pair and 120 Ohm CAN FD transmission lines. | 2026-11-05 | 2026-11-11 | 6 | System Architecture Sign-Off Gate | HIGH | TODO | Hardware Engineering | David Miller
Phase 2: Schematic Capture & Hardware Simulation | Subtask |  | S-Parameter Extraction for USB 2.0 Eye Diagram | Simulate return loss and jitter across frequency sweep. | 2026-11-05 | 2026-11-08 | 3 |  | MEDIUM | TODO | Hardware Engineering | David Miller
Phase 2: Schematic Capture & Hardware Simulation | Subtask |  | Common-Mode Choke Filtering & Insertion Loss Analysis | Verify filter attenuation at 480Mbps harmonic frequencies. | 2026-11-08 | 2026-11-11 | 3 |  | MEDIUM | TODO | Hardware Engineering | David Miller
Phase 2: Schematic Capture & Hardware Simulation | Main Task |  | Schematic Freeze & ERC Audit Gate | Zero electrical rule check errors, cross-net verification, and netlist export. | 2026-11-12 | 2026-11-19 | 7 | High-Speed Differential Impedance Simulation (USB & CAN FD) | URGENT | TODO | Hardware Engineering | Noah Centineo

## Timeline Guide
Column | Required | Description
Phase / Milestone | Optional | Project phase or sprint milestone (e.g. "Phase 1: Architecture"). If left empty, uses Board default sprint or Backlog.
Task Type | Yes | Enter "Main Task" or "Subtask". Any "Subtask" row automatically belongs to the preceding Main Task above it!
Task Key | Optional | Leave blank to auto-create key: PROJECT-TASKTYPE-TEAM-NUMBER (e.g. R-MT-HE-107 or R-MT-GEN-1 for Main Task, and R-ST-HE-107-1 for Subtask), or enter existing key to UPDATE.
Task Title | Yes | Name of the task or subtask activity.
Task Description | Optional | Detailed scope, acceptance criteria, or engineering notes.
Start & End Dates | Optional | Dates in YYYY-MM-DD. Auto-computed using Duration (Days) if one is omitted.
Duration (Days) | Optional | Working duration in days. If Start Date is given, End Date is auto-calculated.
Dependencies / Predecessors | Optional | Title or Key of prerequisite tasks. Automatically wired into Outdid Sync’s DAG dependency graph!
Team & Assignee | Optional | Target discipline and owner. Matches assignee by Name, Email, or "Name <email>".